## Register
DLM Issues Register
Source |  |  |  | Issue Analysis | [11 empty] | Follow-up
Date of report | Recorded by (Name) | Reported by (Name) | Organisation | Issue ID | Issue Description | Issue Primary Category | Other (please specify) | Sub-Categories (if applicable) | Related Issue IDs | Level | Sub-Level | (Potential) Impact (see Definitions) | Relevant to evaluation only? | Resolved? | If resolved, how? (or action taken to date) | Further information required | Action Required | Person Responsible for Action | Status
|  |  |  | IS001 | NBMLHD and WSLHD have been allowing non-indigenous partners/family members to participate in DLM. Decision needs to be made whether to allow this to occur in all new sites. Some sites are not open to this idea. Carla has contacted Chief Investigators for comment. | Patient Population |  |  |  | Site | Evaluation | Low | No | Ongoing
|  |  |  | IS002 | NBMLHD is running the Positively Hep program at the site targeted at general community. Some indigenous community members will be going through the program and receiving education and screening before being offered to go through the DLM program. This could lower the numbers going through screening as part of DLM. Need to ask Felicity how this is being managed - are these clients still being recorded as DLM clients? Is it noted that they took part in Positively Hep? | Patient Population |  |  |  | Site | Evaluation | Low | No | Ongoing | Felicity advised Elena that clients are recorded as having gone through Positively Hep program.
IS003
IS004
IS005
IS006
IS007
IS008
IS009
IS010
IS011
IS012
IS013
IS014
IS015
IS016
IS017
IS018
IS019
IS020
IS021
IS022
IS023
IS024
IS025
IS026
IS027
IS028
IS029
IS030
IS031
IS032
IS033
IS034
IS035
IS036
IS037
IS038
IS039
IS040
IS041
IS042
IS043
IS044
IS045
IS046
IS047
IS048
IS049
IS050
IS051
IS052
IS053
IS054
IS055
IS056
IS057
IS058
IS059
IS060
IS061
IS062
IS063
IS064
IS065
IS066
IS067
IS068
IS069
IS070
IS071
IS072
IS073
IS074
IS075
IS076
IS077
IS078
IS079
IS080
IS081
IS082
IS083
IS084
IS085
IS086
IS087
IS088
IS089
IS090
IS091
IS092
IS093
IS094
IS095
IS096
IS097
IS098
IS099
IS100
IS101
IS102
IS103
IS104
IS105
IS106
IS107
IS108
IS109
IS110
IS111
IS112
IS113
IS114
IS115
IS116
IS117
IS118
IS119
IS120
IS121
IS122
IS123
IS124
IS125
IS126
IS127
IS128
IS129
IS130
IS131
IS132
IS133
IS134
IS135
IS136
IS137
IS138
IS139
IS140
IS141
IS142
IS143
IS144
IS145
IS146
IS147
IS148
IS149
IS150
IS151
IS152
IS153
IS154
IS155
IS156
IS157
IS158
IS159
IS160
IS161
IS162
IS163
IS164
IS165
IS166
IS167
IS168
IS169
IS170
IS171
IS172
IS173
IS174
IS175
IS176
IS177
IS178
IS179
IS180
IS181
IS182
IS183
IS184
IS185
IS186
IS187
IS188
IS189
IS190
IS191
IS192
IS193
IS194
IS195
IS196
IS197
IS198
IS199
IS200
IS201
IS202
IS203
IS204
IS205
IS206
IS207
IS208
IS209
IS210
IS211
IS212
IS213
IS214
IS215
IS216
IS217
IS218
IS219
IS220
IS221
IS222
IS223
IS224
IS225
IS226
IS227
IS228
IS229
IS230
IS231
IS232
IS233
IS234
IS235
IS236
IS237
IS238
IS239
IS240
IS241
IS242
IS243
IS244
IS245
IS246
IS247
IS248
IS249
IS250
IS251
IS252
IS253
IS254
IS255
IS256
IS257
IS258
IS259
IS260
IS261
IS262
IS263
IS264
IS265
IS266
IS267
IS268
IS269
IS270
IS271
IS272
IS273
IS274
IS275
IS276
IS277
IS278
IS279
IS280
IS281
IS282
IS283
IS284
IS285
IS286
IS287
IS288
IS289
IS290
IS291
IS292
IS293
IS294
IS295
IS296
IS297
IS298
IS299
IS300
IS301
IS302
IS303
IS304
IS305
IS306
IS307
IS308
IS309
IS310
IS311
IS312
IS313
IS314
IS315
IS316
IS317
IS318
IS319
IS320
IS321
IS322
IS323
IS324
IS325
IS326
IS327
IS328
IS329
IS330
IS331
IS332
IS333
IS334
IS335
IS336
IS337
IS338
IS339
IS340
IS341
IS342
IS343
IS344
IS345
IS346
IS347
IS348
IS349
IS350
IS351
IS352
IS353
IS354
IS355
IS356
IS357
IS358
IS359
IS360
IS361
IS362
IS363
IS364
IS365
IS366
IS367
IS368
IS369
IS370
IS371
IS372
IS373
IS374
IS375
IS376
IS377
IS378
IS379
IS380
IS381
IS382
IS383
IS384
IS385
IS386
IS387
IS388
IS389
IS390
IS391
IS392
IS393
IS394
IS395
IS396
IS397
IS398
IS399
IS400
IS401
IS402
IS403
IS404
IS405
IS406
IS407
IS408
IS409
IS410
IS411
IS412
IS413
IS414
IS415
IS416
IS417
IS418
IS419
IS420
IS421
IS422
IS423
IS424
IS425
IS426
IS427
IS428
IS429
IS430
IS431
IS432
IS433
IS434
IS435
IS436
IS437
IS438
IS439
IS440
IS441
IS442
IS443
IS444
IS445
IS446
IS447
IS448
IS449
IS450
IS451
IS452
IS453
IS454
IS455
IS456
IS457
IS458
IS459
IS460
IS461
IS462
IS463
IS464
IS465
IS466
IS467
IS468
IS469
IS470
IS471
IS472
IS473
IS474
IS475
IS476
IS477
IS478
IS479
IS480
IS481
IS482
IS483
IS484
IS485
IS486
IS487
IS488
IS489
IS490
IS491
IS492
IS493
IS494
IS495
IS496
IS497
IS498
IS499
IS500
IS501
IS502
IS503
IS504
IS505
IS506
IS507
IS508
IS509
IS510
IS511
IS512
IS513
IS514
IS515
IS516
IS517
IS518
IS519
IS520
IS521
IS522
IS523
IS524
IS525
IS526
IS527
IS528
IS529
IS530
IS531
IS532
IS533
IS534
IS535
IS536
IS537
IS538
IS539
IS540
IS541
IS542
IS543
IS544
IS545
IS546
IS547
IS548
IS549
IS550
IS551
IS552
IS553
IS554
IS555
IS556
IS557
IS558
IS559
IS560
IS561
IS562
IS563
IS564
IS565
IS566
IS567
IS568
IS569
IS570
IS571
IS572
IS573

## Definitions
ISSUE IMPACT
Description | Definition
Negligible | Minimal impact: Issue is expected to have little to no impact on the smooth operation of the project and is noted but doe not require action.
Low | Minor Impact: Issue is expected to have a minor/moderate effect on the project and may require some action.
Medium | Significant Impact: Issue will have an effect on the project and requires significant action.
High | Major Impact: Issue will have a significant/ major effect on the project and requires immediate action.
Extreme | Severe Impact: Issue poses great risk to project. Is places entire project in jeopardy. All project partners must be informed immediately and consulted regarding action taken.
Primary Category | Secondary Category (if applicable) | Sub-Categories (if applicable)
Workforce | Workforce | Technical, Staffing level, Performance, Recruitment, Contractual, Training and development
Budget | Budget | Allocation, Management, Funding Source
Other Resourcing | Other Resourcing
Project Management | Project Management | Contractual, Ethics/Governance, Regulatory, Schedule, Mismanagement
Patient Population | Patient Population | Inmate movements, Access, Safety, Clinical Management, Engagement, Misinformation/education
Data/Information Systems | Data/Information Systems | Access, Management, Confidentiality, Equipment
Security | Security | Training, Protocol Breach, Patient Access, Unacceptable practice
Policy/Procedure Compliance | Policy/Procedure Compliance | Lack of training/knowledge, Discordant priorities, Access
Organisational Structure | Organisational Structure | Bureaucracy, Communication, Contractual
Communications | Communications | Systems, Misinformation, Transparency, Timing
Stakeholder Acceptability | Stakeholder Acceptability | Competing priorities, High-level support, Engagement
Political | Political
Infrastructure | Infrastructure | IT, Clinic facilities